| WML-A13a-E5a&b – WORK SCHEDULE FOR BAT LICENCE |  |
| --- | --- |
| Site name and address (as stated on the application form or licence granted): Old Mount Farm, Magpie Ln, Canterbury CT4 6YD |  |
| Please ensure that the work schedules are S.M.A.R.T and appropriate timescales are provided for each activity, to fit with order of events. |  |
| Complete these schedules to show timings for all categories of work (mitigation and compensation measures), and to show the main construction period. The most common activities are listed here, and you can add up to 6 more if needed. Leave blank if not applicable. Enter timing by stating start and end dates, to nearest month and year (see first lines for examples). Enter comments if you need to clarify timings. For very complex schemes (e.g. high impact or phased development schemes) if additional lines are needed please do add in. This work schedule will form part of any bat licence. E5a |  |

| PLEASE INCLUDE DATE OF SUBMISSION (e.g. 01 July 2016). This will be referenced in the annex |  |  |  |  |  |  |  |  |  |  |  | 15/09/23 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity |  |  |  |  |  | Timing |  |  |  | Comments |  |  |  |  |  |
| Pre- development activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Example: Bat house creation (in advance of licence) |  |  |  |  |  | Sept-14 to Nov-14 |  |  |  | Also put up 3 bat boxes before end of December 2015, in advance of works commencing |  |  |  |  |  |
| Creation of standalone bat feature/s (state completed and fit for purpose if created before licensable works due to commence) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Installation of bat boxes pre-development works (state completed and fit for purpose if created before licensable works due to commence) |  |  |  |  |  | Septmber / Early october 2023 |  |  |  | 2 compensatory bat boxes (2f Schwegler, or similar) to be installed on exisitng mature trees / posts as appropriate. |  |  |  |  |  |
| Permanent exclusion measures (e.g. use of one-way excluders prior to permanent blocking of access points or destruction of roost) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Mid-development activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Example: Capture exercise (e.g. by hand /hand-held nets, etc) |  |  |  |  |  | Sept-2016 |  |  |  | By hand |  |  |  |  |  |
| Pre-works inspection by Named Ecologist or Accredited Agent |  |  |  |  |  | August 2023 to October 2023 or March 2024 to May 2024 |  |  |  | Inspection of B1 |  |  |  |  |  |
| Installation of protective measures (e.g. separation membranes whilst working in lofts) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Disturbance by noise, illumination or vibration (please specify) |  |  |  |  |  | N/A |  |  |  | Bat roost features will be removed prior to main construction works commencing. |  |  |  |  |  |
| Temporary exclusion measures (e.g. use of one-way excluders with access re-instated following works) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Permanent exclusion measures (e.g. use of one-way excluders prior to permanent blocking of access points or destruction of roost) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Capture exercise (e.g. by hand / hand-held nets, etc – please state) |  |  |  |  |  | October / November 2023 or March 2024 to May 2024 |  |  |  | Unlikely to find bats during works. In the unlikely event bats are discovered they may be taken by hand until suitable for release. |  |  |  |  |  |
| Destructive search by soft demolition |  |  |  |  |  | October / November 2023 or March 2024 to May 2024 |  |  |  | Removal of roosting features on Building 1. |  |  |  |  |  |
| During development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Example: Mechanical demolition |  |  |  |  |  | Oct-2016 |  |  |  | Buildings X and Y will be knocked down after sign off from Named Ecologist |  |  |  |  |  |
| Mechanical demolition of all or part of structures (once declared free of bats by Named Ecologist or Accredited Agent) – please state |  |  |  |  |  | November / December 2023 or May 2024 |  |  |  | Building B1 will be demolished once declared free of bats by the Named Ecologist |  |  |  |  |  |
| Construction period start and end dates |  |  |  |  |  | October / November 2023 to October / November 2024 |  |  |  |  |  |  |  |  |  |
| Site checks and maintenance during construction |  |  |  |  |  | N/A |  |  |  | Once the building has been declared free of bats and the building demolished, no further site checks will be required. |  |  |  |  |  |
| Post construction mitigation/compensation on ‘development’ site or other (provide details below) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Example: Installation of access points and bat boxes |  |  |  |  |  | Feb-2017 |  |  |  | Access points will be installed after completion of new roof structure; remaining 3 x bat boxes installed by end of this month. |  |  |  |  |  |
| Creation of mitigation/compensation post development (e.g. installation of bat tubes, bricks, boxes, access points, etc – specify in comments section) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Habitat reinstatement or restoration (following temporary impacts) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| Hedgerow or woodland planting (please specify) |  |  |  |  |  | N/A |  |  |  | N/A |  |  |  |  |  |
| E5b) Post-development works - type a "Y" where each activity will occur for a given year and leave blank for no activity. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year: | 2016 | 2017 | 2018 | 2019 | 2020 |  | 2021 | 2022 | 2023 |  | 2024 |  | 2025 | 2026 | 2027 |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Habitat management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Year: | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| Habitat management |  |  |  |  |  |  |  |  |  |  |  |  |
| Site maintenance |  |  |  |  |  |  |  |  |  |  |  |  |